## 12-Month Calendar
NexusGuard Security Awareness Calendar, FY2026
One theme per month. Core modules (GS) go to all 450 staff; specialist modules go to the IT, Management and Customer-facing tracks. Simulation rounds run every second month. Module codes are in the Module Schedule sheet.
Month | Theme | Objective | Key activities | Target groups | Delivery channels | Responsible parties | Metrics and targets | Compliance link | Phishing simulation
January | Password security and MFA | Make strong passwords, a password manager and MFA the norm, and launch the program. | Program launch message from the CEO and CISO; assign GS-2 Passwords, MFA and password managers (20 min) to all staff; password manager rollout with drop-in clinics; IT-3 Privileged access security for IT staff; nominate security champions (one per team); baseline security culture survey; Data Privacy Day tip (28 Jan). | All staff; IT and Technical staff (privileged access) | LMS e-learning; CEO and CISO email; intranet; drop-in clinics; team huddles | CISO (sponsor); GRC Analyst (program manager); IT Security Manager; HR (LMS); Communications | GS-2 completed by 90% of staff by month end; password manager adopted by 50% of staff; culture survey response 60% or more | ISO A.6.3; HIPAA 164.308(a)(5)(ii)(D); PCI DSS 12.6.1, 12.6.3; NCA ECC 1-10 | No round
February | Phishing Awareness Month | Cut click and credential entry rates and make reporting a habit. | Safer Internet Day launch; assign GS-3 Phishing and social engineering (30 min) to all staff; promote the Report Phishing button; phishing simulation round 1 (late month); weekly "phish of the week" tips; just-in-time 5-minute lesson for anyone who clicks; micro-simulations for new joiners. | All staff; Customer-facing teams (introduction to vishing) | LMS; simulation platform; posters and digital signage; newsletter; intranet | IT Security Manager (simulation); GRC Analyst; HR; Communications | GS-3 completion 95% or more; round 1 click rate 28% or less (baseline 34%); credential entry 12% or less (baseline 18%); report rate measured, target 20% or more | ISO A.6.3; HIPAA 164.308(a)(5)(ii)(B); PCI DSS 12.6.3.1; NCA ECC 1-10 | Round 1
March | Social engineering and business email compromise | Equip executives, finance and customer-facing staff to resist impersonation and payment fraud. | MG-1 Executive BEC workshop (60 min, live); finance payment-verification drill (call-back rule); CF-2 Vishing role-play for customer-facing teams (45 min); GS-4 Social engineering and impersonation (15 min) for all staff; Q1 knowledge pulse quiz (10 questions). | Management and Executives; Finance; Customer-facing teams; All staff | Live workshop; role-play; e-learning; email | CISO; Finance lead; Customer Support lead; GRC Analyst | Executive workshop attendance 90% or more; vishing verification success 70% or more (first run sets baseline); Q1 quiz average 80% or more | ISO A.6.3; PCI DSS 12.6.3.1; HIPAA 164.308(a)(5)(i); NCA ECC 1-10 | No round
April | Data handling, classification and privacy | Teach correct classification and handling of PHI, card data and personal data, and privacy duties. | CF-1 Handling PHI and personal data under HIPAA and GDPR (60 min) for customer-facing teams; GS-5 Data classification and handling (20 min) for all staff, using the quick reference guide; MG-2 Data governance briefing for managers (45 min); phishing simulation round 2; DPO question-and-answer session; "clean-up week" to find and secure stray sensitive files. | Customer-facing teams; All staff; Managers; IT staff (data in tickets and logs) | LMS; live Q&A; quick reference cards; simulation platform | DPO; Compliance Officer; GRC Analyst; IT Security Manager (simulation) | Customer-facing completion 100%; classification quiz average 85% or more; click rate 20% or less; credential entry 8% or less; report rate 35% or more | ISO A.6.3, A.5.12; HIPAA 164.308(a)(5)(i); GDPR Art. 39(1)(b); PCI DSS 12.6.3; NCA ECC 1-10 | Round 2
May | Secure remote work, mobile and travel | Reduce risk from home networks, public Wi-Fi, personal devices and travel. | GS-6 Working securely anywhere (20 min); home-working security self-assessment (per the Acceptable Use Policy); World Password Day (first Thursday) reminder on passphrases; travel security briefing for frequent travelers; BYOD enrollment drive with IT drop-in help. | All staff; Remote and hybrid staff; Frequent travelers | LMS; self-assessment form; email; intranet; IT drop-in | IT Security Manager; IT Operations Manager; HR; GRC Analyst | GS-6 completion 95% or more; self-assessment completion 90% or more; personal devices in the managed container 95% or more; MFA on remote access 95% or more | ISO A.6.3, A.6.7; HIPAA 164.308(a)(5)(ii)(A); PCI DSS 12.6.3.2; NCA ECC 1-10 | No round
June | Secure coding and vulnerability management | Strengthen secure development, patching and secrets handling in the technical teams. | IT-1 Secure coding workshop on OWASP Top 10, secrets and dependencies (4 hours) with hands-on labs; IT-2 Vulnerability management and patch SLAs (90 min); code review clinic; CF-3 Secure communications and verification (20 min); phishing simulation round 3; micro-lesson for all staff on unsafe software and shadow IT. | IT and Technical staff; Customer-facing teams; All staff (micro-lesson) | Workshops; labs; LMS; engineering all-hands; simulation platform | CISO; Engineering lead; IT Security Manager; GRC Analyst | IT workshop completion 95% or more; lab pass mark 80% or more; mean time to patch Critical vulnerabilities 10 days or less; click rate 14% or less; credential entry 5% or less; report rate 45% or more | ISO A.6.3, A.8.25; HIPAA 164.308(a)(5)(ii)(B); PCI DSS 12.6.3, 6.2.2; NCA ECC 1-10 | Round 3
July | Physical security and insider risk | Strengthen clean desk, visitor and tailgating habits, and teach insider risk basics. | GS-7 Physical security and clean desk (15 min); clean desk and screen lock walk-through audits at each office; tailgating test with the security team; security champions drive; reminder to report lost devices within 1 hour; Q3 management security briefing. | All staff; Reception and facilities; Managers | E-learning; floor walks; posters; digital signage | Facilities Manager; Security team; HR; GRC Analyst | GS-7 completion 95% or more; clean desk audit pass 90% or more; tailgating challenge rate 70% or more | ISO A.6.3, A.7.7; HIPAA 164.310(a), (c); PCI DSS 12.6.3, 9; NCA ECC 1-10 | No round
August | Incident reporting and response readiness | Make everyone fluent in reporting and test the technical and executive response. | "See it, report it" campaign on the 1-hour reporting rule; GS-8 Incident reporting (10 min); CF-5 Incident reporting for customer data (15 min); IT-4 Incident response tabletop (2 hours); MG-3 Executive breach tabletop (2 hours) with Legal and the DPO; phishing simulation round 4; recognition for the best reporters. | All staff; IT and Technical staff; Management and Executives; Customer-facing teams | Campaign posters; live tabletops; simulation platform; email | Security Operations Center Manager; CISO; Legal and DPO; GRC Analyst | Tabletop attendance 90% or more; tabletop actions closed within 30 days 80% or more; click rate 10% or less; credential entry 3% or less; report rate 55% or more; median time to report 45 minutes or less | ISO A.6.3, A.5.24 to A.5.26; HIPAA 164.308(a)(6); PCI DSS 12.6.3, 12.10; NCA ECC 1-10 | Round 4
September | Cloud, SaaS and AI safe use | Prevent shadow IT and data leakage through unapproved tools and generative AI. | GS-9 Approved tools and safe AI use (20 min) tied to the Acceptable Use Policy; publish the approved services register; IT-5 Cloud security configuration briefing on public storage and identity (90 min); management data governance reminder; CF-4 Vishing test and refresher; Acceptable Use Policy re-acknowledgment drive. | All staff; IT and Technical staff; Customer-facing teams; Management | LMS; briefing; intranet; question-and-answer with Security | CISO; Head of IT; GRC Analyst; Legal | GS-9 completion 95% or more; Acceptable Use Policy acknowledgment 98% or more; IT briefing attendance 95% or more | ISO A.6.3, A.5.23; HIPAA 164.308(a)(5)(i); PCI DSS 12.6.3.2; NCA ECC 1-10 | No round
October | Cybersecurity Awareness Month | Run a company-wide capstone campaign, reinforce all habits and measure progress. | Month-long campaign with weekly themes (passwords and MFA, phishing, updates, reporting); live webinar with the CISO; phishing simulation round 5; annual knowledge assessment of 20 questions for all staff; optional IT capture-the-flag (IT-6); champions awards; quarterly management briefing; family security tips handout. | All staff; All tracks | All channels; webinar; competitions; intranet | CISO; GRC Analyst; Communications; HR; Security champions | Campaign participation 70% or more; annual assessment completed by 95% with average 85% or more; click rate 7% or less; credential entry 2% or less; report rate 65% or more | ISO A.6.3; HIPAA 164.308(a)(5)(ii)(A); PCI DSS 12.6.3; NCA ECC 1-10 | Round 5
November | Regulatory obligations and third-party risk | Make sure managers and staff understand HIPAA, PCI DSS, GDPR and NCA ECC duties and supplier risks. | MG-4 Regulatory obligations briefing for executives (60 min); GS-11 Compliance refresher for all staff (20 min); supplier and invoice-change fraud awareness for finance and procurement; seasonal scams micro-lesson (shopping and delivery scams); annual policy review reminder. | Management and Executives; Finance and Procurement; All staff | Live briefing; LMS; newsletter | Compliance Officer; DPO; Legal; Procurement; GRC Analyst | Executive attendance 100%; GS-11 completion 95% or more; policy acknowledgment 98% or more | ISO A.6.3, A.5.31; HIPAA 164.308(a)(5)(i); PCI DSS 12.6.3; NCA ECC 1-10, 1-9 | No round
December | Review, recognition and planning | Close the year with evidence, results and lessons, and plan for FY2027. | Phishing simulation round 6 (year-end); annual review of the program's effectiveness (PCI DSS 12.6.2); results to the ISSC and the Board; recognition for champions and top reporters; holiday scam and travel tips; update content from incidents and threat trends; FY2027 plan and budget draft. | All staff; Leadership | Newsletter; ISSC and Board reports; intranet | CISO; GRC Analyst; HR; Finance | Click rate 5% or less; credential entry 1% or less; report rate 70% or more; annual completion 98% or more; program review completed; FY2027 plan approved | ISO A.6.3, 9.1; HIPAA 164.308(a)(5)(i); PCI DSS 12.6.2; NCA ECC 1-10 | Round 6

## Module Schedule
Module Schedule by Track
A dot shows the month a module is assigned. Core modules apply to every employee. Annual hours are formulas over the table.
Code | Track | Module | Format | Minutes | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
GS-1 | Core (all staff) | Security essentials and policies | E-learning | 45 | bar: Jan
GS-2 | Core (all staff) | Passwords, MFA and password managers | E-learning | 20 | bar: Jan
GS-3 | Core (all staff) | Phishing and social engineering | E-learning with simulation | 30 | bar: Feb
GS-4 | Core (all staff) | Social engineering and impersonation | E-learning | 15 | bar: Mar
GS-5 | Core (all staff) | Data classification and handling | E-learning | 20 | bar: Apr
GS-6 | Core (all staff) | Working securely anywhere (remote, mobile, travel) | E-learning | 20 | bar: May
GS-7 | Core (all staff) | Physical security and clean desk | E-learning | 15 | bar: Jul
GS-8 | Core (all staff) | Incident reporting | E-learning | 10 | bar: Aug
GS-9 | Core (all staff) | Approved tools and safe AI use | E-learning | 20 | bar: Sep
GS-10 | Core (all staff) | Annual knowledge assessment (20 questions) | Online assessment | 20 | bar: Oct
GS-11 | Core (all staff) | Compliance refresher (HIPAA, PCI DSS, GDPR) | E-learning | 20 | bar: Nov
IT-1 | IT and Technical | Secure coding workshop (OWASP Top 10, secrets, dependencies) | Classroom and labs | 240 | bar: Jun
IT-2 | IT and Technical | Vulnerability management and patch SLAs | Classroom | 90 | bar: Jun
IT-3 | IT and Technical | Privileged access security | Classroom or e-learning | 90 | bar: Jan
IT-4 | IT and Technical | Incident response tabletop | Tabletop exercise | 120 | bar: Aug
IT-5 | IT and Technical | Cloud security configuration | Classroom | 90 | bar: Sep
IT-6 | IT and Technical | Capture-the-flag challenge (optional) | Hands-on lab | 120 | bar: Oct
MG-1 | Management and Executives | Business email compromise and executive impersonation | Live workshop | 60 | bar: Mar
MG-2 | Management and Executives | Data governance and classification | Briefing | 45 | bar: Apr
MG-3 | Management and Executives | Executive breach tabletop | Tabletop exercise | 120 | bar: Aug
MG-4 | Management and Executives | Regulatory obligations (HIPAA, PCI DSS, GDPR, NCA ECC) | Live briefing | 60 | bar: Nov
MG-5 | Management and Executives | Quarterly security briefing (4 sessions of 20 min) | Briefing | 80 | bar: Jan; Apr; Jul; Oct
CF-1 | Customer-facing | Handling PHI and personal data (HIPAA, GDPR) | Classroom with case studies | 60 | bar: Apr
CF-2 | Customer-facing | Social engineering from customers (vishing role-play) | Role-play workshop | 45 | bar: Mar
CF-3 | Customer-facing | Secure communications and verification procedures | E-learning | 20 | bar: Jun
CF-4 | Customer-facing | Vishing test and refresher | Simulation and coaching | 20 | bar: Sep
CF-5 | Customer-facing | Incident reporting for customer data | E-learning | 15 | bar: Aug
Annual learning hours per person
| Track | Specialist hours | Core hours | Total hours per person
| General Staff | 0 | 3.9167 | 3.9167
| IT and Technical | 12.5 | 3.9167 | 16.4167
| Management and Executives | 6.0833 | 3.9167 | 10
| Customer-facing | 2.6667 | 3.9167 | 6.5833
Phishing simulations run in Feb, Apr, Jun, Aug, Oct and Dec for all staff and are not counted in these hours. IT-6 is optional.

## KPI Tracker
KPI Tracker: targets, actuals and status
Enter actuals (blue) in the middle block as each month closes. Status compares actual with target. Lower is better: Green at or below target, Amber up to 25% above, Red above that. Higher is better: Green at or above target, Amber down to 90% of target, Red below that. Baseline 34% click and 18% credential entry come from the recent simulation.
Monthly targets
KPI | Better | Unit | Baseline | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Phishing click rate | Lower | % | 34% | Feb: 28%; Apr: 20%; Jun: 14%; Aug: 10%; Oct: 7%; Dec: 5%
Credential entry rate | Lower | % | 18% | Feb: 12%; Apr: 8%; Jun: 5%; Aug: 3%; Oct: 2%; Dec: 1%
Phishing report rate | Higher | % | not measured | Feb: 20%; Apr: 35%; Jun: 45%; Aug: 55%; Oct: 65%; Dec: 70%
Repeat clickers (clicked in 2+ rounds) | Lower | % | not measured | Apr: 10%; Jun: 7%; Aug: 5%; Oct: 3%; Dec: 2%
Median time to report a phish (minutes) | Lower | min | not measured | Feb: 90; Apr: 75; Jun: 60; Aug: 45; Oct: 40; Dec: 30
Assigned training completed on time | Higher | % | not measured | 90% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 98%
Average quiz or assessment score | Higher | % | not measured | Mar: 80%; Apr: 85%; Jun: 85%; Sep: 85%; Oct: 85%
New joiners trained within 30 days | Higher | % | not measured | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Actuals (enter here)
KPI | Better | Unit | Baseline | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Phishing click rate | Lower | %
Credential entry rate | Lower | %
Phishing report rate | Higher | %
Repeat clickers (clicked in 2+ rounds) | Lower | %
Median time to report a phish (minutes) | Lower | min
Assigned training completed on time | Higher | %
Average quiz or assessment score | Higher | %
New joiners trained within 30 days | Higher | %
Status (calculated)
KPI | Better | Unit | Baseline | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Phishing click rate | Lower | %
Credential entry rate | Lower | %
Phishing report rate | Higher | %
Repeat clickers (clicked in 2+ rounds) | Lower | %
Median time to report a phish (minutes) | Lower | min
Assigned training completed on time | Higher | %
Average quiz or assessment score | Higher | %
New joiners trained within 30 days | Higher | %

## Phishing Trajectory
Phishing simulation: target trajectory
Targets by simulation round, from the recent baseline. Report rate was not measured in the baseline.
Round | Click rate | Credential entry rate | Report rate
Baseline | 34% | 18%
Feb (R1) | 28% | 12% | 20%
Apr (R2) | 20% | 8% | 35%
Jun (R3) | 14% | 5% | 45%
Aug (R4) | 10% | 3% | 55%
Oct (R5) | 7% | 2% | 65%
Dec (R6) | 5% | 1% | 70%

## About
About this workbook
Purpose: the 12-month calendar for the NexusGuard Security Awareness Program (FY2026), supporting the Security Awareness Program Plan.
Sheets: 12-Month Calendar (themes, activities, groups, channels, owners, metrics); Module Schedule (modules by track and month, with annual hours); KPI Tracker (targets, actuals, status); Phishing Trajectory (targets and chart).
Audience: General Staff (320), IT and Technical staff (65), Management and Executives (35) and Customer-facing teams (30), 450 in total.
Baseline: the recent simulation found 34% clicked and 18% entered credentials. The last training was 22 months ago.
Status rules: see the note on the KPI Tracker sheet. Blue text is an input. Targets are proposals for approval by the CISO.
Data note: NexusGuard is a fictional company, and all plans, targets and figures are for portfolio use.